## Android_UserApp_Status_Tracker
Task ID | Category | Page Name | Start Date | End Date | Status | Progress (%) | Comments
1 | User Pages | Registration Page | 2025-01-15 | 2025-01-20 | In progress | 20 | Initial design phase
2 | User Pages | Login Page | 2025-01-20 | 2025-01-25 | Completed | 100 | Backend integration pending
3 | User Pages | Home Page | 2025-01-25 | 2025-01-30 | In progress | 50 | UI design in progress
4 | User Pages | Laundry Studio Profile Page | 2025-01-30 | 2025-02-04 | Completed | 100 | Laundry Studio Profile Page development task completed
5 | User Pages | Services Profile Page | 2025-02-05 | 2025-02-10 | Not Started | 0
6 | User Pages | Cart Page | 2025-02-10 | 2025-02-15 | Not Started | 0
7 | User Pages | Checkout Page | 2025-02-15 | 2025-02-20 | Not Started | 0
8 | Profile Pages | Edit Profile Page | 2025-02-20 | 2025-02-24 | In progress | 30 | Pending kick-off
9 | Profile Pages | My Activities Page | 2025-02-25 | 2025-02-28 | In progress | 50 | Scheduled after design
10 | Profile Pages | Addresses Page | 2025-03-01 | 2025-03-04 | Not Started | 0 | Requirements under review
11 | Profile Pages | Payment and Refund Page | 2025-03-05 | 2025-03-09 | Not Started | 0
12 | Profile Pages | Settings Page | 2025-03-10 | 2025-03-14 | Not Started | 0
13 | Profile Pages | Send Feedback Page | 2025-03-15 | 2025-03-19 | In progress | 40
14 | Profile Pages | Refer Page | 2025-03-20 | 2025-03-24 | Not Started | 0
15 | Profile Pages | Skawsh for Studios Page | 2025-03-25 | 2025-03-29 | Not Started | 0
16 | Profile Pages | Support Page | 2025-03-30 | 2025-04-03 | In progress | 70
17 | Orders Pages | Current Orders Page | 2025-03-01 | 2025-03-05 | Not Started | 0 | Initial planning phase
18 | Orders Pages | Past Orders Page | 2025-03-05 | 2025-03-10 | Not Started | 0 | Backend development pending
19 | Favourites Pages | Laundry Studio Page | 2025-04-01 | 2025-04-05 | Not Started | 0 | Pending design approval
20 | Favourites Pages | Laundry Service Page | 2025-04-05 | 2025-04-10 | Not Started | 0 | Development phase
21 | Services Pages | Service List Page | 2025-04-15 | 2025-04-20 | Completed | 100 | Initial planning phase